|  | EUROPEAN COMMISSION JOINT RESEARCH CENTRE Institute for Health and Consumer Protection Consumer Products Safety and Quality |
| --- | --- |

Ispra, 12-09-2008

Doc. CA/50/2008

5th Meeting of the REACH Competent Authorities

25-26 September 2008

Venue: Centre A. Borschette, Room 2A; Rue Froissart, 36; B-1040 Brussels

Concerns: 	RIP 3.6 Progress Report

Agenda item:	4.1

Action Requested:	The REACH Competent Authorities are invited to take note of the progress report on the Technical Guidance Document on Classification and Labelling in accordance with the Globally Harmonised System (RIP 3.6).

1	Introduction

The following sections give an overview of the available draft guidance documents and propose a time schedule for their finalisation. In general, it is proposed that the working groups finalise as many draft guidance documents during or shortly after their meetings in September-October-November 2008. Subsequently, the SEG will be asked to approve sections of the guidance documents, hazard class by hazard class, either in a written procedure or at a meeting.

For some hazard classes, where UN updates are foreseen, or where the finalisation of guidance would go beyond RIP 3.6 (March 2009), it is proposed to temporarily postpone the discussions. That should make it easier to focus the efforts on the guidance that can be finalised within the RIP 3.6 time lines. For these hazard classes, the continuation of the discussion will depend on the European Chemicals Agency, which is responsible for the guidance.

CPS&Q (ex ECB) proposes to schedule an additional SEG Meeting at the beginning of December 2008, for the preliminary approval of several guidance documents, and to try to approve the guidance of some hazard classes in a written procedure for the SEG in October 2008. All hazard classes will have to be officially approved by the SEG in March 2009.

2	Physical hazards, WG1

A compilation of all available guidance documents was sent to WG1 members on 18 July 2008. WG1 experts were requested to consider the SEG comments, to provide comments to this compilation, and to revise their chapters by 29 August 2008. CPS&Q will provide a new compilation in the beginning of September.

There is one further meeting of WG1 on 21-22 October 2008.

2.1	Finalisation of guidance for physical hazards

At the 21-22 October 2008 WG1 meeting the compilation guidance document for physical hazards will be discussed as a whole, section by section (hazard class by hazard class). The text on the different hazard classes will have to be approved by WG1 experts. Sections of hazard classes that need minor amendments will have to be updated shortly after the meeting. Approved hazard classes will be proposed to be preliminary approved by the SEG in December 2008. The SEG may propose further amendments, in which case final approval must take place in March 2009.

A few physical hazard classes will need further work. Those will be proposed for approval at the SEG meeting in March 2009 as well.

Preliminary approval of physical hazards guidance in December 2008

The following physical hazard classes are foreseen to be approved by WG1 at the 21-22 October 2008 meeting, and could therefore be preliminary approved by the SEG in December 2008, when the contents are agreed by SEG experts.

| Hazard Class | Document / Status |
| --- | --- |
| Explosives | Document: ECBI/53/05 Add. 1 Status: Draft / 16-04-2007 |
| Flammable Gases | Document: ECBI/47/07 Revision 1 Status: Draft / 27-03-2008 |
| Flammable Aerosols | Document: ECBI/13/08 Status: Draft / 11-04-2008 |
| Oxidising Gases | Document: ECBI/47/07 Revision 1 Status: Draft / 27-03-2008 |
| Gases under Pressure | Document: ECBI/47/07 Revision 1 Status: Draft / 27-03-2008 |
| Flammable Liquids | Document: ECBI/51/05 Add. 1, Revision 1 Status: Draft / 06-06-2008 |
| Flammable Solids | Document: ECBI/50/05 Add. 1 Status: Draft / ? |
| Self reactives | Document: ECBI/25/04 Add. 1, Revision 1 Status: Draft / 21-05-2008 |
| Self heating substances & mixtures | Document: ECBI/64/07 Status: Draft / 28-11-2007 |
| Water reactives | Document: ECBI/46/07 Status: Draft / 19-06-2007 |
| Oxidising solids and liquids | Document: ECBI/17/08 Status: Draft / 17-04-2008 |
| Organic peroxides | Document: ECBI/21/04 Add1, Revision 1 Status: Draft / 22-05-2008 |
| General guidance physical hazards * | Document: ECBI/05/07 Status: Draft / 01-05-2007 |

* The general guidance for physical hazards in document ECBI/05/07 is foreseen to be used for RIP 3.6 Module 1.

Approval of physical hazards guidance in March 2009

The following physical hazard classes need further work. Therefore they are proposed to be approved in March 2009.

| Hazard class | Document / status | Work to be done | Timelines |
| --- | --- | --- | --- |
| Pyrophoric solids and liquids | Document: - Status: - | Develop examples | 3 October first draft 21-22 October meeting November 2008 draft update January 2009 final draft |
| Corrosivity to metals | Document: ECBI/32/08 Status: Draft / 30-07-08 | Present first draft | 19 September re-draft 3 October comments 21-22 October meeting November 2008 draft update January 2009 final draft |
| Other physical hazard classes to which SEG had comments in December 2008. |  |  | ? |

Input to other WGs

WG4 requested the input of WG1 experts to the guidance document for the use of the Translation Table in Annex VII to the CLP Regulation. The updated document ECBI/39/08 will be sent to WG1 to be discussed at the 21-22 October 2008 meeting.

3	Health hazards, WG2

A compilation of health hazards is not made, because the document would be too large to handle in an easy manner. The sections for the health hazards will be kept separately. It was agreed by WG2 that no guidance would be needed for respiratory sensitisation and aspiration hazard.

There are two further meetings planned for WG2, on 24-26 September 2008 and in January 2009. However, it should be attempted to finalise the guidance of some of the hazard classes already by December 2008.

3.1	Finalisation of guidance for health hazards

At the 24-26 September 2008 WG2 meeting the draft guidance documents for health hazards will be discussed, hazard class by hazard class. The text on the different hazard classes will have to be approved by WG2 experts. Sections of hazard classes that need minor amendments will have to be updated shortly after the meeting. Approved hazard classes will be proposed to be preliminary approved by the SEG in December 2008. The SEG may propose further amendments, in which case final approval must take place in March 2009.

A few health hazard classes will need further work. Those will be proposed for approval at the SEG meeting in March 2009 as well.

This section will need to be updated with the contributions received for the 24-26 September 2008 meeting.

Preliminary approval of health hazards guidance in December 2008

The following health hazard classes are foreseen to be approved by WG2 at the 24-26 September 2008 meeting, and could therefore be preliminary approval by the SEG in a written procedure or at a SEG meeting in December 2008, when the contents are agreed by SEG experts.

| Hazard Class | Document / Status |
| --- | --- |
| Acute Toxicity | Document: ECBI/31/08 Status: Draft / 18-07-2008 |
| Skin corrosion & irritation | Document: ECBI/69/07 Add. 1, Revision 1 Status: Draft / 30-06-2008 |
| Germ cell mutagenicity | Document: ECBI/75/07 Revision 1 Status: Draft / 23-05-2008 |
| Reprotoxicity, Lactation | Document: ECBI/117/06 Revision 1 Status: Thought starter / 13-09-2007 |
| Specific Target Organ Toxicity, Single Exposure | Document: ECBI/03/08 Status: Draft / 10-01-2008 |
| Specific Target Organ Toxicity, Repeated Exposure | Document: ECBI/04/08 & Add. 1 (metals) Status: Drafts / 10-01-2008 & 16-07-2008 |

The health hazard classes for which the guidance will not be agreed at the September 2008 WG2 meeting and for which further work seems to be needed, cannot be approved by the SEG in 2008.

Approval of health hazards guidance in March 2009

The following health hazard classes need further work. Therefore they are proposed to be approved in March 2009. For serious eye damage / eye irritation, guidance is under development and will be presented to WG2 when ready.

A subgroup to WG2 was created for Reprotoxicity potency considerations and setting of specific concentration limits. This group is establishing a database for developmental effects and effects on fertility, and investigates if cut off limits can be identified for more or less potent reprotoxic substances. It is expected that this research will be finished within the timelines of RIP 3.6. A back to back meeting is foreseen with the January 2009 WG2 meeting.

| Hazard Class | Document / Status |
| --- | --- |
| Carcinogenicity | Document: ECBI/30/08 Status: Draft / 30-05-2008 |
| Serious eye damage / eye irritation | Document: - Status: In preparation |
| Reprotoxicity potency considerations and setting of SCLs | Document: - Status: Under investigation and discussion by WG2 sub-group |
| Other health hazards that need further work, as a result of the September 2008 WG2 meeting, cannot be approved in 2008. |  |

Health hazard classes that need further work

It is foreseen that the classification criteria for skin sensitisation will be updated in the UN purple book, and that the UN subcommittee for classification and labelling adopts these criteria in December 2008. The EU will then implement these criteria into the CLP Regulation, with the 1st or 2nd ATP. It is proposed to temporarily postpone the further development of this guidance document, until implementation of these new criteria at UN level.

Maternal toxicity has in the past been an area needing guidance. Also under the CLP Regulation, guidance would be needed. No expert has so far been appointed to take this task on board. Therefore this issue is for the moment proposed to be postponed.

Therefore, for these hazard classes it can at this stage not be predicted if they can be approved in December 2008 or March 2009 or not.

| Hazard class | Document / status | Work to be done | Timelines |
| --- | --- | --- | --- |
| Skin Sensitisation: | Document: ECBI/20/08 and Adds 1 and 2 Status: Draft / 23-05-2008 | Align first draft with new criteria. | After publication of new criteria in the purple book |
| Reprotoxicity, Maternal toxicity | Document: ECBI/30/04 Status: SE report / 26-03-2004 | Rewrite specialised experts report into guidance | ? So far no volunteer to do this work. |

3.2	Finalisation of guidance for general health issues

Preliminar approval of general health guidance in December 2008

| General issue | Document / Status |
| --- | --- |
| Corrosive Substances & other hazard classes | Document: ECBI/77/07 Revision 1 Status: Draft / 23-05-08 |

Approval of general  health guidance in March 2009

WG2 and the SEG agreed that RIP 3.3 contains sufficient and up to date guidance for read across, grouping and categorisation that could be used for each individual hazard class. Sue Hubbard will write general guidance on read across, grouping and categorisation for RIP 3.6 health hazards.

It was agreed at the January 2008 WG2 meeting that guidance for non-standard species should not be developed at this stage. Therefore that issue was withdrawn from the work program of WG2.

| General issue | Document / Status |
| --- | --- |
| Read Across, Grouping & Categorisation | Document: RIP 3.3 Status: In preparation |
| Biological availability, Metals | Document: ECBI/29/08 Status: Draft / 16-06-08 |
| Bridging principles | Document: ECBI/73/07 Revision 1 Status: Thought starter / 30-06-08 |

4	Environmental hazards, WG3

The chapter on aquatic toxicity was subdivided into sections for which different authors volunteered to draft the guidance. A working group was established for the classification of mixtures. A compilation of all chapters was sent to WG3 experts on 5 July 2008.

WG3 experts felt that streamlining of the document would be needed before the 12-13 November WG3 meeting. Furthermore, the mixtures working group proposed to meet as well, to resolve some open issues with mixtures classification for aquatic toxicity. Therefore a meeting of a small number of WG3 experts was organised by Johannes Tolls and Diederik Schowanek, which took place in London on 1 and 2 September 2008. The compiled guidance document was streamlined and the open issues with Mixtures classification were resolved. General guidance was taken out of the compilation and is proposed to be included in a general introduction to RIP 3.6.

It will have to be decided after the November 2008 meeting if an additional Environment meeting is needed in the beginning of 2009. It should, however, be attempted to have a WG3 agreement on the guidance at the November meeting, a preliminary written approval by the SEG in January 2009, and approval by the SEG in March 2009.

| Hazard Class | Document / Status |
| --- | --- |
| Aquatic Toxicity | Document: ECBI/22/08 Add. 1 Status: Draft / 05-07-2008 |

| General issue | Document / Status |
| --- | --- |
| Biological availability, environment | Document: ECBI/33/08 Rev. 2 Status: Draft / 01-09-2008 (by Tom Gebel & Alicja Anderson, WG4) |

5	General / combined issues, WG4

It was agreed that WG4 would start creating a Frequently Asked Question list, with the answers and that CPS&Q would compile the list. This list will be dynamic until the end of RIP 3.6. It is the aim that this list will be provided together with the general module 1 guidance on the ECHA homepage. The FAQ list should cover issues that are not currently covered by the guidance.

The SEG thought the contents of ECBI/76/06 Revision 4 (on the split entry concept for substances that may emerge as aerosols) were too specific, and beyond the scope of RIP 3.6. Therefore further development of this guidance is not foreseen under RIP 3.6, but a reference was proposed to be added to the acute toxicity section. General guidance for form or physical state will be developed by WG4 experts.

There is one further meeting foreseen for WG4, which is currently scheduled for 25-27 November 2008. It is proposed to postpone the November 2008 WG4 meeting to the beginning of 2009, since the work of WG4 depends more on the developments in WG2 and WG3 than at first expected. Furthermore, the precautionary statements need a more substantial amount of input from WG4 experts than expected. This proposal will have to be discussed within the Commission first before providing a revised meeting schedule for RIP 3.6.

| General issue | Document / Status |
| --- | --- |
| Mixtures, general guidance in RIP 3.6 | Document: - Status: P. Keymolen, A. Anderson, W. Cameron offered to write first draft |
| Mixtures, bridging principles | Document: - Status: Await developments in WG2 and 3 |
| Mixtures within Mixtures | Document: ECBI/35/08 Status: Thought starter ECBI/35/08 will not be further developed in guidance. T. Gebel will provide very general guidance. |
| Biological availability | Document: ECBI/33/08 Rev. 2 Status: Draft / 01-09-2008 |
| Form or physical state | Document: ECBI/38/08 Status: Draft / 01-09-2008 |
| Setting of Specific Concentration Limits | Document: ECBI/34/08 Status: Thought starter, to be updated and then partly transferred to Module-1. |
| Labelling | Document: - Status: First draft in preparation by labelling sub-group of WG4 |
| Use of Annex VII, limitations | Document: ECBI/39/08 Status: Draft / 12-08-2008. To be updated. |